## Tracker
Data Preparation Roadmap Tracker
Phase-based tracker adapted from the stakeholder roadmap. Use this sheet to assign owners, update progress, and manage blockers while keeping the roadmap sequence visible.
Source HTML: file:///Users/adhitanjung/Documents/AITech/ringan-fs/ringan-data/public/data-preparation-roadmap.html
Tracker rule The spreadsheet is the working tracker. Update status, owner, progress, blockers, and next actions here as the roadmap moves. |  |  | Full scope 50 problems |  |  | Pilot gate 8–10 problems |  |  | Decision rule Start once the first slice is usable — not once all 50 problems are finished.
Tracked phases |  | Done |  | In progress |  | Average progress |  | Flagged phases
Phase | Phase Focus | Title | Scope / Objective | Exit Criteria | Status | Owner | Progress % | Dependencies / Blockers | Next Action | Flag Type | Flag Detail | Phase 0 | Phase 1 | Phase 2 | Phase 3 | Phase 4 | StartIdx | EndIdx
Phase 0 | Pre-work readiness | Complete taxonomy pre-work | The four-week clock assumes taxonomy pre-work is already done. If not, add a Phase 0 milestone before Phase 1 begins. | Taxonomy pre-work is complete and the schema is confirmed stable before active build starts. | Conditional |  | 0% | Explicitly confirm the data schema is frozen. An unstable model during Waves 2–3 can invalidate pilot work entirely. | Confirm whether Phase 0 is needed and, if yes, assign an owner before Phase 1 starts. | Assumption | Conditional milestone only if taxonomy pre-work is not already complete before Phase 1. | ■ |  |  |  |  | 0 | 0
Phase 1 | Taxonomy lock | Freeze taxonomy & review rules | Lock the 50 problems, naming conventions, stable IDs, and approval criteria before any content work begins. | 50 problems, naming conventions, stable IDs, and approval criteria are locked. | Not Started |  | 0% | One week is aggressive for taxonomy consensus. Name an explicit owner and pre-agree a tiebreaker before the clock starts. | Assign the taxonomy owner and pre-agree a tiebreaker for unresolved decisions. | PM risk | One week is aggressive for taxonomy consensus. Name an explicit owner and pre-agree a tiebreaker before the clock starts. |  | ■ |  |  |  | 1 | 1
Phase 2 | Pilot build | Build the pilot slice | Prepare the first 8–10 problems with full assessments and at least one suggestion each. | The first 8-10 problems are prepared with full assessments and at least one suggestion each. | Not Started |  | 0% | Who owns this build? Accountability is invisible. Add a named DRI before this wave is confirmed. | Name the DRI and start building the pilot slice in the spreadsheet tracker. | Missing item | Who owns this build? Accountability is invisible. Add a named DRI before this wave is confirmed. |  |  | ■ |  |  | 2 | 2
Phase 3 | Pilot validation | Test the flow & fix gaps | Run the pilot end-to-end. Find missing fields, broken relations, and unclear wording. Patch before expanding. | Pilot validation passes or unresolved gaps are explicitly accepted before expansion. | Not Started |  | 0% | Define "done." What's the pass threshold? What failure triggers a re-do vs. a patch-and-proceed? | Define the pass threshold and test the pilot end to end against it. | Missing item | Define "done." What's the pass threshold? What failure triggers a re-do vs. a patch-and-proceed? |  |  |  | ■ |  | 3 | 3
Phase 4 | Batch expansion | Expand in batches | Add remaining problems in 10–15 item waves. Repeat the same build → test → fix loop each time. | Remaining problems are added in controlled batches with the same build-test-fix loop. | Not Started |  | 0% | Explicitly confirm the data schema is frozen. An unstable model during Waves 2–3 can invalidate pilot work entirely. | Freeze the schema and prepare the next 10-15 item expansion batch. | Assumption | Assumes data schema is stable. If the model is still in flux, pilot results may be invalidated mid-build. |  |  |  |  | ■ | 4 | 4
Operating rules
Working rule | Build · test · fix · expand. Each batch must be fully usable before the next one starts. No skipping ahead.
Schema dependency | Explicitly confirm the data schema is frozen. An unstable model during Waves 2–3 can invalidate pilot work entirely.
Decision chips | Test early ¦ Fix before expanding ¦ Repeat in waves
Note on C12: Source: file:///Users/adhitanjung/Documents/AITech/ringan-fs/ringan-data/public/data-preparation-roadmap.html Original label: W0 / Before Week 1 Section: Tracker translation: Phase 0
Note on C13: Source: file:///Users/adhitanjung/Documents/AITech/ringan-fs/ringan-data/public/data-preparation-roadmap.html Original label: W1 / Week 1 Section: Tracker translation: Phase 1 from W1
Note on C14: Source: file:///Users/adhitanjung/Documents/AITech/ringan-fs/ringan-data/public/data-preparation-roadmap.html Original label: W2 / Week 2 Section: Tracker translation: Phase 2 from W2
Note on C15: Source: file:///Users/adhitanjung/Documents/AITech/ringan-fs/ringan-data/public/data-preparation-roadmap.html Original label: W3 / Week 3 Section: Tracker translation: Phase 3 from W3
Note on C16: Source: file:///Users/adhitanjung/Documents/AITech/ringan-fs/ringan-data/public/data-preparation-roadmap.html Original label: W4 / Week 4+ Section: Tracker translation: Phase 4 from W4

## Source Notes
Source Notes
Source HTML: file:///Users/adhitanjung/Documents/AITech/ringan-fs/ringan-data/public/data-preparation-roadmap.html
Section | Item | Detail
Tracker translation | Primary adaptation | Converted week labels into phase labels and added tracker columns for status, owner, progress, blockers, and next action.
Principle | Principle 1 | 8–10 problems to start
Principle | Principle 2 | 3–5 assessments per problem
Principle | Principle 3 | 1 suggestion minimum
Principle | Principle 4 | Usable before expanding
Release gate | Full scope | 50 problems
Release gate | Pilot gate | 8–10 problems
Release gate | First usable slice | Do not wait for all 50 problems to be complete. Release requires only enough data to test the flow end to end — not a finished taxonomy.
Info card | Working rule | Build · test · fix · expand. Each batch must be fully usable before the next one starts. No skipping ahead.
Info card | Pre-wave assumption | The four-week clock assumes taxonomy pre-work is already done. If not, add a Wave 0 milestone before Week 1 begins.
Info card | Schema dependency | Explicitly confirm the data schema is frozen. An unstable model during Waves 2–3 can invalidate pilot work entirely.
Decision rule | Primary rule | Start once the first slice is usable — not once all 50 problems are finished.
Decision chip | Chip 1 | Test early
Decision chip | Chip 2 | Fix before expanding
Decision chip | Chip 3 | Repeat in waves
Phase mapping | Phase 1 | W1 / Week 1 -> Taxonomy lock
Phase mapping | Phase 2 | W2 / Week 2 -> Pilot build
Phase mapping | Phase 3 | W3 / Week 3 -> Pilot validation
Phase mapping | Phase 4 | W4 / Week 4+ -> Batch expansion
Footer | Label | Ringan Data · Stakeholder roadmap · 2026